TASK BREAKDOWN

Implementation Plan For Bidirectional Scroll Animation

| Product | Gym Growth Platform - Bidirectional Scroll Animation System |
| --- | --- |
| Version | v1.0 |
| Status | Draft for design, engineering, QA, and implementation |
| Date | May 28, 2026 |
| Reviewers | Albert Saputra, UI/UX Designer, Frontend Engineer, QA Engineer, Performance Reviewer |
| Core Requirement | Animasi harus tetap aktif saat user scroll ke bawah dan saat user scroll balik ke atas, dengan performa stabil dan respect prefers-reduced-motion. |

1. Epic Breakdown

| Epic | Description | Owner |
| --- | --- | --- |
| E1 Motion System | Build reusable scroll direction and observer controller. | Frontend |
| E2 CSS Presets | Create animation classes, reduced motion, responsive variants. | Frontend + Design |
| E3 Site Integration | Apply to 20 gym pages and key modules. | Frontend |
| E4 QA & Performance | Validate no jank, no broken CTA, no mobile overflow. | QA |
| E5 Documentation | Document usage, do/don't, and acceptance checks. | Product |

2. Task List

| ID | Task | Acceptance | Estimate |
| --- | --- | --- | --- |
| T-01 | Audit current reveal/parallax code | List current selectors and one-shot behavior. | 0.5d |
| T-02 | Create ScrollMotionController | Direction, observer, enter/exit state working. | 1d |
| T-03 | Add CSS bidirectional presets | scroll-up and scroll-down classes visually distinct but subtle. | 1d |
| T-04 | Add reduced motion fallback | All transform/parallax disabled under prefers-reduced-motion. | 0.5d |
| T-05 | Integrate with modules | Hero, platform, benchmark, facility, gallery, plans, join animate. | 1d |
| T-06 | Mobile tuning | No horizontal overflow; motion lighter under 768px. | 0.5d |
| T-07 | Interaction regression | Menus, modals, tabs, forms, WhatsApp generator still work. | 1d |
| T-08 | 20-site batch validation | All build-check scripts pass. | 0.5d |
| T-09 | Visual QA | Check at least representative sites: chain, hardcore, wellness, cafe, local. | 1d |
| T-10 | Documentation update | README/report explains motion system and how to tune presets. | 0.5d |

3. Sprint Plan

| Sprint | Focus | Deliverable |
| --- | --- | --- |
| Sprint 1 | Core motion engine and CSS tokens | Controller + presets in one site. |
| Sprint 2 | Batch integration | 20 pages updated and build passed. |
| Sprint 3 | QA and polish | Visual review, mobile tuning, accessibility pass. |

4. Definition Of Done

All 20 sites pass build/validation.

Scroll down and scroll up both trigger visible animation changes.

Reduced motion is respected.

No broken buttons, modals, gallery, or WhatsApp generator.

No horizontal overflow on mobile.

Implementation notes are documented.

5. Detailed 10-Sprint Breakdown

| Sprint | Duration | Goal | Output |
| --- | --- | --- | --- |
| 1 | 1 week | Audit current animation and interaction code. | Motion audit matrix and bug list. |
| 2 | 1 week | Create shared motion tokens and CSS presets. | styles.css motion layer. |
| 3 | 2 weeks | Build ScrollMotionController. | Direction-aware observer and lifecycle classes. |
| 4 | 2 weeks | Integrate benchmark site. | One fully working representative landing page. |
| 5 | 2 weeks | Apply to chain/modern gyms. | FTL, Fitness Plus, FITX, Osbond tuned. |
| 6 | 2 weeks | Apply to local/community gyms. | Evolution, Planet, New Icon, M Gym, DM Gym tuned. |
| 7 | 2 weeks | Apply to hardcore/performance gyms. | Draco, SpeedRocky, Warriors, BlackBox, Champion tuned. |
| 8 | 2 weeks | Apply to wellness/cafe/women-focused gyms. | Belle Crown, Crystal, OCIGEN, Optimum, Glanzfit tuned. |
| 9 | 3 weeks | QA, accessibility, mobile, performance. | Bug fixes and validation report. |
| 10 | 3 weeks | Polish, documentation, deployment prep. | Production-ready batch and handover notes. |

6. RACI

| Workstream | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Motion system | Frontend Engineer | Tech Lead | UI Designer, QA | Product Owner |
| Visual tuning | UI Designer | Creative Director | Brand Strategist | Frontend Engineer |
| Copy and data | Brand Strategist | Product Owner | Researcher | Sales/Admin |
| Accessibility | QA Engineer | Tech Lead | UI Designer | Product Owner |
| Deployment | Frontend Engineer | Tech Lead | QA | Product Owner |

7. QA Task Checklist

Check scroll down reveal on hero, facilities, membership, gallery, location, FAQ, final CTA.

Check scroll up re-entry from footer back to hero.

Check reduced motion with browser/OS setting.

Check keyboard: nav, modal, FAQ, gallery, package selector, CTA.

Check mobile 390px and desktop 1440px.

Check all buttons: WhatsApp, Maps, Instagram, package selector, class/facility tabs.

Check image hover/tap paragraph descriptions.

Check no broken images, no fallback logo unless source missing.

8. Implementation Deliverables

| Deliverable | Format | Owner | Done When |
| --- | --- | --- | --- |
| Motion system code | script.js + styles.css | Frontend | Reusable and documented. |
| Updated landing pages | 20 static sites | Frontend | All sections integrated. |
| Validation script | build-check.mjs | Frontend/QA | Fails on missing essentials. |
| QA report | Markdown | QA | Lists pass/fail per gym. |
| Handover docs | README + specs | Product | Non-technical user can understand next steps. |